## dsmp-task-management
DSMP Task Management Group 5
Phase 1 Project Initial
Name | Owner | Priority | Status | Timeline - Start | Timeline - End | Comment
1.1 Kick-off meeting of DSMP | Chloe Chen Wenqi, Isaac, Zhang Shuhao | Low | Done | 2021-02-09 | 2021-02-09
1.2 Team greeting | Chloe Chen Wenqi, Isaac, Zhang Shuhao | Medium | Done | 2021-02-14 | 2021-02-14
1.3 Develop Project Chater | Chloe Chen Wenqi, Isaac, Zhang Shuhao | High | Done | 2021-02-14 | 2021-02-20 | Outcome: Project Chater #v
|  |  |  | 2021-02-09 | 2021-02-20
Phase 2 Project Planning
Name | Owner | Priority | Status | Timeline - Start | Timeline - End | Comment
2.1 Requirement Analysis | Chloe Chen Wenqi | Low | Done | 2021-02-20 | 2021-02-21
2.2 Task Decomposition | Zhang Shuhao | High | Done | 2021-02-25 | 2021-02-27
2.3 Task Allocation | Isaac | Medium | Done | 2021-02-27 | 2021-02-27
2.4 Develop Detailed Project Plan | Chloe Chen Wenqi, Isaac, Zhang Shuhao | Medium | Done | 2021-02-27 | 2021-03-01 | Outcome: Project Plan #v
|  |  |  | 2021-02-20 | 2021-03-01
Phase 3 Implementation
Name | Owner | Priority | Status | Timeline - Start | Timeline - End | Comment
1st Exploration | Isaac | Medium | Done | 2021-03-01 | 2021-03-15
Evaluation and Testing | Chloe Chen Wenqi, Isaac, Zhang Shuhao | High | Done | 2021-03-16 | 2021-03-16
2nd Exploration | Chloe Chen Wenqi | Medium | Done | 2021-03-16 | 2021-04-01
Evaluation and Testing | Chloe Chen Wenqi, Isaac, Zhang Shuhao | High | Done | 2021-04-01 | 2021-04-02
3rd Exporation | Zhang Shuhao | Medium | Done | 2021-04-02 | 2021-04-30
Evaluation and Testing | Chloe Chen Wenqi, Isaac, Zhang Shuhao | High | Done | 2021-05-01 | 2021-05-02 | Outcome: Various Performances #v
|  |  |  | 2021-03-01 | 2021-05-02
Phase 4 Project Control
Name | Owner | Priority | Status | Timeline - Start | Timeline - End | Comment
4.1 Progress Monitor | Isaac | Medium | Done | 2021-03-15 | 2021-04-30
4.2 Quality Deliverables | Zhang Shuhao | Medium | Done | 2021-04-01 | 2021-04-30
4.3 Report to DSMP logsheet | Chloe Chen Wenqi | Medium | Done | 2021-02-20 | 2021-05-01
|  |  |  | 2021-02-20 | 2021-05-01
Phase 5 Project Closure
Name | Owner | Priority | Status | Timeline - Start | Timeline - End | Comment
5.1 Approaches Integration | Chloe Chen Wenqi, Isaac, Zhang Shuhao | High | Done | 2021-04-23 | 2021-05-01
5.2 Performance valuation and acceptance | Chloe Chen Wenqi, Isaac, Zhang Shuhao | Medium | Done | 2021-05-01 | 2021-05-07
5.3 Report Integration | Chloe Chen Wenqi, Isaac, Zhang Shuhao | Medium | Done | 2021-05-07 | 2021-05-14
5.4 Project Delivery | Chloe Chen Wenqi, Isaac, Zhang Shuhao | Low | Done | 2021-05-14 | 2021-05-14 | Outcome: Deliver finish #v
5.5 Project Summary | Chloe Chen Wenqi, Isaac, Zhang Shuhao | High | Done | 2021-05-18 | 2021-05-18
|  |  |  | 2021-04-23 | 2021-05-18